## Slide 1: SoI Student Project Review
Team: Retro Roots | Lead: Swathmika S S
Members: Umamageshwari, Subhasini, Subetha, Sarvajit SoI Mentor: NandhaKumar | SoI Vertical: CD | Cohort/Batch: 2024 - 28
Telemedicine Access for Rural Healthcare – Nabha

## Slide 2: Problem & End User Identification
End User: Daily-wage laborers & farmers in Nabha's 173 villages. Low digital literacy.
Problem Trigger:
Need for a medical consultation. Traveling to the understaffed Nabha Civil Hospital risks lost wages and an unsuccessful visit
.
Evidence:
  Nabha Civil Hospital: 11/23 doctors (<50% staffed).
  31% of rural Punjab households have internet.
  User interviews confirm travel is often wasted.
Success Metrics:
  50% reduction in patient travel time/cost.
  70% successful first-attempt consultations.
  90% user satisfaction in low-bandwidth tests.

## Slide 3: Problem Description
▶ Rural residents of Nabha, Punjab, lack reliable healthcare access. The primary hospital is critically understaffed, serving 173 villages with only 11 doctors. Patients undertake long, costly journeys, only to often find specialists unavailable or medicines out of stock. This results in delayed treatment, worsened health, and financial loss for daily-wage earners. Poor internet connectivity further limits digital solutions.

## Slide 4: Proposed Solution
Connects rural patients with certified doctors via secure video/audio/chat
Enables appointment scheduling and digital prescriptions
Stores patient data in cloud-based EMR for easy access
Includes AI Symptom Checker for early diagnosis & triage
Integrates pharmacy & preventive health modules
Supports offline mode for low-connectivity rural areas
Powered by AWS Cloud, React Native/React.js, Node.js/Django REST, and Python ML

## Slide 5: Literature Survey (Research)
Source (APA/IEEE) | Year | Key Insight / Method | Gap Relevant to Our Problem
WHO – Digital Health Strategy | 2021 | Emphasizes telemedicine for underserved areas | No localized solution for rural India.
Journal of Telemedicine & e-Health | 2022 | AI improves diagnosis in remote consultations | Limited real-time triage in rural setups
Indian Ministry of Health Reports | 2020 | Lack of infrastructure affects rural care access | No integrated EMR & digital tools in villages
IEEE Studies on mHealth Apps | 2023 | Mobile apps enhance chronic care management | Poor offline support & literacy challenges

## Slide 6: Existing Solutions (Products/Services)
10 Sep
2025
Feature / Criteria | Product A | Product B | Product C | Our Approach
Target User | Rural & urban patients | Urban smartphone usersHealth record users | Health record users | Rural Nabha patients
Core Function | Basic video consult | Teleconsult + monitoring | EMR storage | Telemed + AI triage + EMR
Accuracy/Performance | Limited diagnosis | No AI triage | No consult feature | AI-based alerts
Cost | Free (Govt) | Paid (subscription) | Freemium | Low-cost, community-based
Deployment | Web & mobile | Subscription app | Cloud EMR | React, AWS, scalable
Data/Privacy | Govt servers | Proprietary cloud | Basic encryption | AES-256, HIPAA, RBAC
Known Limitations | Poor UI, low scale | Needs fast net | No AI/consult | Offline, integrated AI & EMR

## Slide 7: Our Unique Selling Proposition (USP)
Value Prop: Reliable, first-time-right healthcare access that saves time and money, even offline.
Differentiators:
  Offline-First Core: Health records & symptom checker work without internet.
  Local Pharmacy Integration: Real-time medicine stock updates for Nabha.
  Low-Bandwidth Optimized: Lightweight app with Punjabi/Hindi voice UI.
Why Now: Post-COVID telemedicine acceptance + documented Nabha crisis.
Feasibility: Skills in Android dev, low-literacy UX. Data from partner pharmacy APIs/SMS.

## Slide 8: Project Plan & Timeline
Phase | Start–End | Milestones/Deliv erables | Evidence of Validation
Problem Validation | 01-Oct → 15-Oct | Identify rural healthcare gaps in Nabha | Interviews with villagers, ASHA workers
Ideation | 16-Oct → 15-Nov | Define key features | Brainstorming with mentors, domain experts
Proof of Concept (PoC) | 16-Nov → 15-Dec | Demo of AI symptom checker + EMR UI | Feedback from rural health volunteers
Prototype | 16-Dec → 15-Jan | Working version with video consults & patient app | Usability testing with beta users
Minimum Viable Product (MVP) | 16-Jan → 10-Feb | Cloud-hosted version with EMR, AI, | Beta testing, feedback forms, early metrics
Final Product | 11-Feb → 28-Feb | Final launch | Adoption analytics

## Slide 9: Risks, Assumptions & Dependencies
Risk: Low Digital Literacy.
Mitigation: Voice-first UI, icon-based navigation.
Risk: Unreliable Internet.
  Mitigation: Offline-first design philosophy.
Risk: Doctor/Pharmacy Buy-in.
  Mitigation: Demonstrate value with MVP; start with pilot partners

## Slide 10: References
Govt. of Punjab. (2024). Health Infrastructure Report, Nabha.
Ministry of Statistics. (2023). Household Social Consumption.
WHO. (2021). mHealth Guidelines.
Kumar & Srivastava. (2022). Journal of Health Informatics in Developing Countries
Govt. of Punjab. (2024). Health Infrastructure Report, Nabha.
Ministry of Statistics. (2023). Household Social Consumption.
WHO. (2021). mHealth Guidelines.
Kumar & Srivastava. (2022). Journal of Health Informatics in Developing Countries